## Sheet1
Date | Project | Module | Activity Description | Hours
2019-09-01 |  |  | Sunday
2019-09-02 |  |  | Ganpati Holiday
2019-09-03 | RMS | RMS | Given issue tested for mobile view | 4
2019-09-03 | RMS | Login | Changes given by shivkumar for done in new password section. | 5
2019-09-04 | RMS | Login | Test the given Chnages | 9
2019-09-05 | RMS | all | Changes in views for option nd search bar for mobile view | 9
2019-09-06 | RMS | all | cadding loader to entire project where needed. | 9
2019-09-07 |  |  | Saturday
2019-09-08 |  |  | Sunday
2019-09-09 | RMS | Contact | Upload Contact csv file | 9
2019-09-10 | RMS | all | assigne changes from sheet (4,5,8,9,15) | 9
2019-09-11 | RMS | Master | chnages in master-task type | 4
2019-09-11 | RMS | Email | added default from element in compose and createtemplate | 5
2019-09-12 | RMS | Setup | changes in company menu and lead history window implemented
2019-09-13 | RMS | Task | changesin task view and create ,added task title coloum in task_master table
2019-09-14 |  |  | Saturday
2019-09-15 |  |  | Sunday
2019-09-16 | RMS | Master | Task type--adding autoadd feature | 5
2019-09-16 | RMS | Email | Email from tab added as per requirment for admin and superuser | 4
2019-09-17 | RMS | Task | Task view adding filter section inprogress--(half day due to electricity issue)
2019-09-18 | RMS | Task | Task filter Section added | 4
2019-09-18 | RMS | Contact | Added chekbox for Inactive user | 3
2019-09-18 | RMS | Contact | Remove Lead status add added to CreateLead as Inquiry Status | 2
2019-09-19 | RMS | Issue | Issue solved from sheet | 9
2019-09-20 | RMS | Issue | Issue solved from sheet | 9
2019-09-21 |  |  | Saturday
2019-09-22 |  |  | Sunday
2019-09-23 | LMS | Login | only Html of login,register,pipeline,login,mclr,follwup | 9
2019-09-24 | LMS | Register | Register | 9
2019-09-25 | LMS | Login | Login | 9
2019-09-26 | LMS | master | branch master,emplpyee master | 9
2019-09-27 | LMS | Pipeline | Pipepline | 9
2019-09-28 |  |  | Saturday
2019-09-29 |  |  | Sunday
2019-09-30 | LMS | Master | Property,Loantype,Loan SubType | 9